## Sheet1
APPLICANT:
PROJECT NAME:
PIN:
|  | Unit Price | Unit of Measure | Quantity | TOTAL | MUSEUM GRANT | APPLICANT (Cash and In-Kind) | OTHER FUNDING SOURCE - | SCHEDULE Start - Complete
Grant Elements
Non-Construction
| Exhibit Design | 250 | HOUR | 8 | 2000 | 2000 |  |  | Mar-May 2021
| Permitting | 0 |  |  | 0
| Project Management | 30 | HOUR | 160 | 4800 |  | 4800 |  | Mar 2021-May 2022
Construction
| Materials & Supplies | 7000 | LS | 1 | 7000 | 7000 |  |  | Aug-Sep 2021
| Exhibit Installation | 1200 | LS | 1 | 1200 | 1200 |  |  | Sep-Oct 2021
| Delivery Costs | 300 | LS | 1 | 300 | 300 |  |  | Aug 2021
Programmatic Costs
| Virtual Curriculum Development-Consultant | 125 | HOUR | 68 | 8500 | 8500 |  |  | Apr-May 2021
| Outreach/Recruitment Costs | 25 | HOUR | 84 | 2100 | 2100 |  |  | Mar-Sept 2021
| Materials, Equipment and Supplies | 10500 | LS | 1 | 10500 | 10500 |  |  | May-Jun 2021
Overhead Costs (not to exceed 15% of total direct costs) |  |  |  |  | 4400 | 4400
Contingency (not to exceed 10%) |  |  |  |  | 4000 | 4000
| GRAND TOTAL |  |  |  | 44800 | 40000 | 4800 | 0
*Overhead costs are allowable and limited to 15% of total direct costs of the grant. In service payroll may not include a “billable rate” or administrative cost allocation. *All invoices and receipts for all project expenditures from all funding sources will be retained and made available in the event of any future State Audits.